## Phase-Wise-Estimate (hidden)
Estimation Management - Phasewise Estimate Release ID: FPS - Estimation.xls C3: Protected Controlled Copy Project ID: CR - Estimation / Ver: 1.0
Phase | Activity Details | Object # | Person days | Participants | Days
Requirement Gathering KT Phase | KT session on Master tables Day 1 ( 2 hrs KT, 4 hrs analysis, 2 hrs questions and answers section) | 14 | 3 | ETL Lead, BI lead, SIT lead | 1
| KT session on Master tables Day 2 | 14 | 3 | ETL Lead, BI lead, SIT lead | 2
| KT session on Transactional tables Day 3 | 9 | 3 | ETL Lead, BI lead, SIT lead | 3
| KT session on Transactional tables Day 4 | 10 | 3 | ETL Lead, BI lead, SIT lead | 4
| KT session on 8 cubes Day 5 | 10 | 3 | ETL Lead, BI lead, SIT lead | 5
Requirement Gathering Analysis and Freezing requirement | Day 1 (understanding document), Deciding on the approach FM Dimensional Model, feasibilty study | 55 ETL 8 cubes | 3 | ETL Lead, BI lead, SIT lead | 6
| Day 2 (understanding document) |  | 3 | ETL Lead, BI lead, SIT lead | 7
| Day 3 (understanding document) |  | 3 | ETL Lead, BI lead, SIT lead | 8
Design Data Model Design | Day 1 (ER diagram) Identifes exact number of warehouse tables and mappings | 65 ETL 8 cubes | 2 | ETL Lead, BI lead | 9
| Day 2 (ER diagram) |  | 2 | ETL Lead, BI lead | 10
| Day 3 (ER diagram) |  | 2 | ETL Lead, BI lead | 11
All ELC documents preparation | Design document, Traceability document |  | 8 | ETL Lead, BI lead
CUT Phase | DB Objects | 65 ETL 8 Dimention Model | #REF!
| ETL |  | #REF! | ELT team
| BI |  | #REF! | BI team
SIT | Round 1 of SIT will be performed |  | #REF! | SIT team
UAT/fixes | Exact UAT scope to be decided during requirement gathering and estimation to be revisited |  | 15 | 2ETL ,1 BI
Go Live | 2 days 2 resource for each day 1 ETL, 1 BI |  | 0 | ETL Lead, BI lead
Estimation value |  |  | #REF!
20% Contingency |  |  | #REF!
Total Estimation value |  |  | #REF!
Total amount in yen (1 USD = 100 yen) |  |  | #REF!
Developing dimensional model for reports takes more time. So it will have no shcedule and dead line. If Report should be similar to that of existing cube, we need to implement drill down in the report. Feasibility study should be completed for all possible cases. Performance issue can be seen because of drill down option. Multiple reports has to be created based on dimension and facts if drill down option is not considered.
| Complexity % | # of objects
| Simple | 28 | 43.08%
| Medium | 29 | 44.62%
| Complex | 8 | 12.31%
Note on B16: Complexity 50% simple 50% medium
Note on A22: requiremen gathering to CUT

## Drop1 (hidden)
| 2014 |  |  | 2015 | [11 empty] | 2016
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26
Analysis of Source system & Identification of rules for data cleansing | bar: 2014 M1 to 2015 M15
Data Model (SID - Common Data Model) | bar: 2014 M1 to 2015 M15
DefineCleansing and Transformation rules | bar: 2014 M1 to 2015 M15
Mapping for Extract of Source and Loading (Abinitio) | bar: 2014 M1 to 2015 M15
Perform Profiling & data cleansing in staging layer | bar: 2014 M1 to 2015 M15
Transformation Mapping Development ( Abinitio) | bar: 2014 M1 to 2015 M15
Error handling and Reconciliation | bar: 2014 M1 to 2015 M15
Management of fallout records | bar: 2014 M1 to 2015 M15
Support for SIT (Multiple Run on data migration) | bar: 2014 M1 to 2015 M15
System Testing | bar: 2014 M1 to 2015 M15
Operation Support, Warranty Support | bar: 2014 M1 to 2015 M15
Migration roll back | bar: 2014 M1 to 2015 M15
Onsite
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director

## Drop0 (hidden)
|  | 2014 |  |  | 2015 | [11 empty] | 2016
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47
Project Inititaion | bar: 2014 M1
Requirement Gathering | bar: 2014 M1 to 2014 M3
Design Phase | bar: 2014 M3 to 2015 M6
Analysis of Source system & Identification of rules for data cleansing | bar: 2014 M3
Source Interface specification finilization | bar: 2015 M4
Data Model (SID - Common Data Model) | bar: 2015 M4
DefineCleansing and Transformation rules | bar: 2015 M4
Customer Account Consolidation Approch | bar: 2015 M5
Migration roll back strategy | bar: 2015 M5
Target Interface specification finilization | bar: 2015 M5
Design Phase | bar: 2015 M5 to 2015 M6
ETL Low level Design | bar: 2015 M7; 2015 M10; 2015 M13; 2016 M16; 2016 M19; 2016 M22; 2016 M26 to 2016 M29
Error Handling an recon Low level design | bar: 2015 M7; 2015 M10; 2015 M13; 2016 M16; 2016 M19; 2016 M22; 2016 M26 to 2016 M29
Customer Account Consolidation Low level design | bar: 2015 M7; 2015 M10; 2015 M13; 2016 M16; 2016 M19; 2016 M22; 2016 M26 to 2016 M29
Coding and Unit Testing
Development source to Landing Area Data syncing Scripts | bar: 2015 M8; 2015 M11; 2015 M14; 2016 M17; 2016 M20; 2016 M23; 2016 M27 to 2016 M30
Development of ETL - Data Profiling and cleansing | bar: 2015 M8; 2015 M11; 2015 M14; 2016 M17; 2016 M20; 2016 M23; 2016 M27 to 2016 M30
Development to handle fallout records | bar: 2015 M8; 2015 M11; 2015 M14; 2016 M17; 2016 M20; 2016 M23; 2016 M27 to 2016 M28
Development Reconciliation Scripts | bar: 2015 M8; 2015 M11; 2015 M14; 2016 M17; 2016 M20; 2016 M23; 2016 M27 to 2016 M28
Physicalize Common Data Model | bar: 2015 M8; 2015 M11; 2015 M14; 2016 M17; 2016 M20; 2016 M23; 2016 M27 to 2016 M28
Loading Common Data Model | bar: 2015 M8 to 2015 M9; 2015 M11 to 2015 M12; 2015 M14 to 2015 M15; 2016 M17 to 2016 M18; 2016 M20 to 2016 M21; 2016 M23 to 2016 M24; 2016 M27 to 2016 M29
System Testing
Testing of ETL and Reconciliation Scripts/reports | bar: 2015 M8 to 2015 M9; 2015 M11 to 2015 M12; 2015 M14 to 2015 M15; 2016 M17 to 2016 M18; 2016 M20 to 2016 M21; 2016 M23 to 2016 M24; 2016 M27 to 2016 M30
Testing of Transformation schema | bar: 2015 M8 to 2015 M9; 2015 M11 to 2015 M12; 2015 M14 to 2015 M15; 2016 M17 to 2016 M18; 2016 M20 to 2016 M21; 2016 M23 to 2016 M24; 2016 M27 to 2016 M30
Testing of fallout records | bar: 2015 M8 to 2015 M9; 2015 M11 to 2015 M12; 2015 M14 to 2015 M15; 2016 M17 to 2016 M18; 2016 M20 to 2016 M21; 2016 M23 to 2016 M24; 2016 M27 to 2016 M30
System Integration an Preprod Support | bar: 2015 M10; 2015 M13; 2016 M16; 2016 M19; 2016 M22; 2016 M25 to 2016 M26; 2016 M29; 2016 M31
Operantional and Warranty Support | bar: 2015 M11 to 2016 M22
Onsite
Drop 0 | Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5
Drop 0 | Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5
Drop 0 | Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5
Drop 0 | Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5
Drop 0 | Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5
Drop 0 | Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5
Drop 0 | Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5
Drop 0 | Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5
Drop 0 | Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5
Drop 0 | Programmer Analyst
Programmer Trainee
Programmer
| Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director
Account Manager (Billed)
Director
Sr. Director
Offshore
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
| Sr. Associate | 2014 M1: 3; 2014 M2: 3; 2014 M3: 3; 2015 M4: 3; 2015 M5: 3; 2015 M6: 3
| Manager | 2014 M1: 2; 2014 M2: 2; 2014 M3: 2; 2015 M4: 2; 2015 M5: 2; 2015 M6: 2
SPM | bar: 2014 M1 to 2015 M6
As. Director | bar: 2014 M1 to 2015 M6
Account Manager (Billed)
Director
| Sr. Director | 2014 M1: 0.5; 2014 M2: 0.5; 2014 M3: 0.5; 2015 M4: 0.5; 2015 M5: 0.5; 2015 M6: 0.5

## Res Load - Summary (hidden)
Drop 0 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 1 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 2 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 3 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 4 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 5 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 6 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 7 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 8 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 9 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total
Drop 10 | 2014 |  | 2015 |  | 2016 |  | 2017 |  | 2018
| Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite | Offshore | Onsite
Estimated Man months | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Programmer Analyst Trainee
Programmer Analyst
Programmer Trainee
Programmer
Associate
Sr. Associate
Manager
SPM
As. Director
Account Manager (Billed)
Director
Sr. Director
Total

## Cover Page
Comcast DeepDive Estimation
New Project Estimation Template
C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled copy

## Summary
Sl No | Phase | Total ( In Mandays)
1 | Analysis of Source system & Identification of rules for data cleansing | 100.8
2 | Data Model (Target Data Model) | 420
3 | BA effort (Cleansing and Transformation rules) | 315
4 | Mapping for Extract of Source and Loading (Abinitio)
5 | Perform Profiling & data cleansing in staging layer
6 | Transformation Mapping Development ( Abinitio)
7 | Error handling and Reconciliation |  | 20 % of total Development effort
8 | Management of fallout records |  | 5 % of total Development effort
10 | Support for SIT (Multiple Run on data migration)
11 | System Testing
12 | Operation Support, Warranty Support
14 | Migration roll back
Total Effort in Person Days
Total Pmonths

## Overall1 (hidden)
| R34 | R5 |  | % Distribution
SIT | 635 | 158.75 | 25% | 26.12% |  | S. No | Phase | Effort (Person Days)
Start Up | 15 | 0 |  | 0.4936% |  | 1 | Project Startup | 14.999 | 0.4936%
PEC | 66.5 | 0 |  | 2.188% |  | 2 | Requirements Gathering & Analysis | 143.9903 | 4.738%
RqM | 144 | 0 |  | 4.738% |  | 3 | Design | 440.9702 | 14.51%
Design | 441 | 0 |  | 14.51% |  | 4 | Construction & Unit Testing | 1429.753 | 47.05%
CUT | 1375 | 55 | 4% | 47.05% |  | 5 | System & Integration Testing | 793.6964 | 26.12%
Delivery | 2 | 2 |  | 0.1316% |  | 6 | Delivery | 3.9997 | 0.1316%
Acc Testing | 35 | 8.75 | 25% | 1.44% |  | 7 | Implementation Support | 11.9992 | 0.3949%
Impl Support | 6 | 6 |  | 0.3949% |  | 8 | Acceptance Testing | 43.747 | 1.44%
PIS | 70 | 0 |  | 2.303% |  | 9 | Post Implementation Support | 69.9953 | 2.303%
Proj Closure | 5 | 0 |  | 0.1645% |  | 10 | Project Execution & Control | 66.4955 | 2.188%
QA Support | 14 | 0 |  | 0.4607% |  | 11 | Project Closure | 4.9997 | 0.1645%
Person Days | 2808.5 | 230.5 | 3039 |  |  | 12 | QA Support | 13.9991 | 0.4607%
Person Hours | 22468 | 1844 | 24312 |  |  |  | Total Project Effort | 3038.7949
Person Days (without Rqmts and Design) | 2253.5 | 1844 | 2484 | 14.2187
|  |  | 19872 | 17.3955 | Final Rate
|  | Simple | Medium | Complex | Total
|  | 112 | 110 | 56 | 278
Assumed Productivity (Code Units/Person Day) |  | 0.33333 | 0.18182 | 0.11765
# of P Days / Code Unit |  | 3 | 5.5 | 8.5
Effort / Complexity |  | 336 | 605 | 476 | 1417
|  |  |  | Buffer for CUT (1%) | 1429.753

## Input Sheet
Sl No | Line & Type of Business | Application Name | Target Application | No of Tables | Remarks
1 | Clinical Management | Admission / Recert / Issues Tracking System | Crescendo | 100 | BLOB/CLOB
2 | Clinical Back Office | CARES | eCW | 100
3 | Clinical Back Office | Interim Tracking System | SAM | 50

## Janus_Estimation
JANUS Estimation
Migration Estimation Summary | Total in Mandays | [6 empty] | Effort in Percentage
Requirement | 240 | [6 empty] | Requirement | 15%
Design | 400 | [6 empty] | Design | 25%
Coding | 640 | [6 empty] | Coding | 40%
Unit Testing | 320 | [6 empty] | Unit testing | 20%
SIT & UAT | 0
Total Effort ( Person days) | 1600
Estmating Factors Migration Procedures/Mappings ( Person Days )
Phase/Complexity | Simple | Medium | High | Complex | Very Complex
Requirement | 0.225 | 0.525 | 0.675 | 0.825 | 1.65
Design | 0.375 | 0.875 | 1.125 | 1.375 | 2.75
Coding | 0.6 | 1.4 | 1.8 | 2.2 | 4.4
Unit testing | 0.3 | 0.7 | 0.9 | 1.1 | 2.2
SIT& UAT | 0 | 0 | 0 | 0 | 0
Total | 1.5 | 3.5 | 4.5 | 5.5 | 11
|  | Staging - Data Extraction & Loading | [5 empty] | Transformation-Target Loading | [6 empty] | Input field
Migration System | Simple | Medium | High | Complex | Very Complex | Total | Simple | Medium | High | Complex | Very Complex | Total |  |  | Complexity - Split Extract & Loading to Staging Layer | Percentage
Admission / Recert / Issues Tracking System | 60 | 30 | 0 | 10 | 0 | 100 | 20 | 40 | 0 | 40 | 0 | 100 |  |  | Simple | 60%
CARES | 60 | 30 | 0 | 10 | 0 | 100 | 20 | 40 | 0 | 40 | 0 | 100 |  |  | Medium | 30%
Interim Tracking System | 30 | 15 | 0 | 5 | 0 | 50 | 10 | 20 | 0 | 20 | 0 | 50 |  |  | High | 0%
Managed Care Browser | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Complex | 10%
OASIS Web Browser | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Very Complex | 0%
Online Patient Record (OPR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Complaints | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Complaints Tracking | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Wound Care | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Complexity - Split Transformation-Target Loading | Percentage
Right Program, Right Time | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Simple | 20%
Visit Accumulation System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Medium | 40%
Climate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | High | 0%
Account Receivable Management System (ARMS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Complex | 40%
ADT (Admission, Discharge and Transfer) System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Very Complex | 0%
Daily Care Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Discharge Letters | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EZCare | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foothold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HC Plus | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IVANS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MD Orders Tracking/Master Log Continues Clients | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nurse Assessment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Partners in Care Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCRS Host | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service Charge Processing (SCP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Suncoast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Incident Tracking System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Scheduling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Homegrown TMG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCRS Host | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCRS Mobile | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Migration Estimation - Data Extraction & Loading | [5 empty] | Migration Estimation - Transformation Mappings
Application | Phase | Simple | Medium | High | Complex | Very Complex | Total | Simple | Medium | High | Complex | Very Complex | Total | Grand Total
Admission / Recert / Issues Tracking System | Requirement | 13.5 | 15.75 | 0 | 8.25 | 0 | 37.5 | 4.5 | 21 | 0 | 33 | 0 | 58.5 | 96
| Design | 22.5 | 26.25 | 0 | 13.75 | 0 | 62.5 | 7.5 | 35 | 0 | 55 | 0 | 97.5 | 160
| Coding | 36 | 42 | 0 | 22 | 0 | 100 | 12 | 56 | 0 | 88 | 0 | 156 | 256
| Unit testing | 18 | 21 | 0 | 11 | 0 | 50 | 6 | 28 | 0 | 44 | 0 | 78 | 128
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 90 | 105 | 0 | 55 | 0 | 250 | 30 | 140 | 0 | 220 | 0 | 390 | 640
CARES | Requirement | 13.5 | 15.75 | 0 | 8.25 | 0 | 37.5 | 4.5 | 21 | 0 | 33 | 0 | 58.5 | 96
| Design | 22.5 | 26.25 | 0 | 13.75 | 0 | 62.5 | 7.5 | 35 | 0 | 55 | 0 | 97.5 | 160
| Coding | 36 | 42 | 0 | 22 | 0 | 100 | 12 | 56 | 0 | 88 | 0 | 156 | 256
| Unit testing | 18 | 21 | 0 | 11 | 0 | 50 | 6 | 28 | 0 | 44 | 0 | 78 | 128
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 90 | 105 | 0 | 55 | 0 | 250 | 30 | 140 | 0 | 220 | 0 | 390 | 640
Interim Tracking System | Requirement | 6.75 | 7.875 | 0 | 4.125 | 0 | 18.75 | 2.25 | 10.5 | 0 | 16.5 | 0 | 29.25 | 48
| Design | 11.25 | 13.125 | 0 | 6.875 | 0 | 31.25 | 3.75 | 17.5 | 0 | 27.5 | 0 | 48.75 | 80
| Coding | 18 | 21 | 0 | 11 | 0 | 50 | 6 | 28 | 0 | 44 | 0 | 78 | 128
| Unit testing | 9 | 10.5 | 0 | 5.5 | 0 | 25 | 3 | 14 | 0 | 22 | 0 | 39 | 64
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 45 | 52.5 | 0 | 27.5 | 0 | 125 | 15 | 70 | 0 | 110 | 0 | 195 | 320
Managed Care Browser | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OASIS Web Browser | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Online Patient Record (OPR) | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Complaints | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Complaints Tracking | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Wound Care | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Right Program, Right Time | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Visit Accumulation System | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Climate | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Account Receivable Management System (ARMS) | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ADT (Admission, Discharge and Transfer) System | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Care Report | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Discharge Letters | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EZCare | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foothold | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HC Plus | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IVANS | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MD Orders Tracking/Master Log Continues Clients | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nurse Assessment | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OPS | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Partners in Care Schedule | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCRS Host | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service Charge Processing (SCP) | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Incident Tracking System | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Patient Scheduling | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Homegrown TMG | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCRS Host | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PCRS Mobile | Requirement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Coding | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unit testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SIT& UAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Effort
Complexity definition factors - Transformation Mappings
Simple
1. Less than 3 tables used in the source to target routines or mapping 2. No Major logic and the business rules are less complex 3. Expected volume <= 1/2 million across 1 or 2 tables
Medium
1. 1 -2 control tables process required 2. 2-4 tables used in the routines or transformation to load target tables 3. Additional Intermediate table along with logic 4. No Major complexity in the data flow or processing logic 3. Expected volume <= 1/2 million across tables
High
1. 1 -3 control tables process required 2. 3-5 tables used in the routines or transformation to load target tables 3. Transformation with high complexity or procedure / functions with moderate to high complexity 4. Moderate changes in the data flow or processing logic 5. Inclusion of additional loops and error handling 6. Expected voulme < = 1 million across multiple tables
Complex
1. 1 -4 control tables process required 2. 5-7 tables used in the routines or transformation to load target tables 3. Transformation with complex business rules or procedure / functions with high complexity 4. Major changes in the data flow or processing logic 5. Inclusion of additional loops and error handling 6. Expected voulme > 1 million across multiples tables
Very Complex
1. 2 -5 control tables process required 2. 7-8 tables used in the routines or transformation to load target tables 3. Transformation with very high complexity with very complex business rules or procedure / functions with very high complexity 4. Complex changes in the data flow or processing logic 5. Inclusion of additional loops and error handling 6. Expected voulme > 2 million across multiples tables

## Estimation_Assumptions
1 | Estimations are based on to available partial list of inventory
2 | This estimation does not include the SIT & UAT support estimates
3 | We don’t have the complexity of the business rule for estimations.
4 | complexity of mappings or routines are purely assumptions based
5 | This estimation includes analysis & development of target data model for each of the application
6 | Estimation for data mappings from the source to target is included
7 | Effort in % for each of the mappings or routines are as follows
Requirement : 15%
Design : 25%
Coding : 40%
Unit testing : 20%
8 | This estimation includes
a.) Extract from source to Staging ( Loading)
b.) development of Data Profiling and Data Cleansing routines
c.) Development of Transformation mappings
d.) Unit Testing
9 | Estimation for DQ (Reconcillation, Matching) are based on to the assumption on the total development efforts
10 | Effort for simple/medium/complex/very complex is as per Cognizant standards
11 | Any additional activity will be estimated seperately
12 | Business analyst effort is not part of this estimate and need to factored seperately
13 | Loading Transformed data is the responsibility of Respective application Owners
14 | Complexity Split Up for Extract and Loading Simple : 50% Medium : 40% High : Complex : 10% Very Complex : 0%
15 | Complexity Split Up for Transformation Simple : 20% Medium : 40% High : 0% Complex : 40% Very Complex :0%
16 | As the migration happening in Drop wise the estimation factors are split across drops for the Transformations
17 | Staging and Transformation has been proportioned for the total inventory against the source / target system for a particular Drops

## ChangeHistory
Change History
| Standard Template |  | Comcast Migration Estimation Template | Create Date: | 2016-01-26 | Update Date:
| Document Title : |  |  | Created by: | DOD | Updated by: |  | DOD
| Version : |  | 0.1
Date | Version | Revision Comments |  |  |  |  | Updated by
2016-01-26 | 1 | Initial version

## Annexture
No. | Application Name | Application Layer | Platform | System Type | Application Description | Owner | Status | Target App | Target Platform
1 | Admission / Recert / Issues Tracking System | Clinical Management | AIX |  | Issues tracking related to admissions and recertifications | AVM | Retire | Crescendo | SaaS
2 | CARES | Clinical Back Office | AIX |  | Web- based application that supports the assignment of field staff | AVM | Retire | eCW | Wintel
3 | Interim Tracking System | Clinical Back Office | AIX |  | Inventory tool | AVM | Retire | SAM | SaaS
4 | Managed Care Browser | Clinical Back Office | AIX |  | Confirmation of fiscals, authorizing services and processing managed care reports | AVM | Retire | eCW | Wintel
5 | OASIS Web Browser | Clinical Management | AIX |  | Web application for completion of OASIS clinical assessments | AVM | Retire | Crescendo | SaaS
6 | Online Patient Record (OPR) | Clinical Management | AIX |  | Web Based Application.PPS System Clinical Nursing Audit Print App | AVM | Retire | eCW | Wintel
7 | Patient Complaints | Clinical Back Office | AIX |  | Web- based clinical application used to track agency wide patient complaints | AVM | Retire | ITMC | AIX
8 | Patient Complaints Tracking | Clinical Back Office | AIX |  | Compliance tracking application | AVM | Retire | ITMC | AIX
9 | Patient Wound Care | Clinical Management | AIX |  | Web application for clinical review of wound images in back office | AVM | Retire | SAM | SaaS
10 | Right Program, Right Time | Clinical Back Office | AIX |  | Ensure appropriate patient assignment | AVM | Retire | eCW | Wintel
11 | Visit Accumulation System | Clinical Back Office | AIX |  | Web based Application | AVM | Retire | eCW | Wintel
12 | Climate | Clinical Management | Ax |  | Web Application, CMH Case Management | AVM | Retire | eCW | Wintel
13 | Account Receivable Management System (ARMS) | Clinical Back Office | Mainframe | Homegrown | Accounts Receivables System used to track billing and receivables information | AVM | Retire | eCW | Wintel
14 | ADT (Admission, Discharge and Transfer) System | Clinical Management | Mainframe | Homegrown | Clinical Admission System | AVM | Retire | eCW | Wintel
15 | Daily Care Report | Clinical Back Office | Wintel | Homegrown | Partners in Care VB.NET web application | AVM | Retire | eCW | Wintel
16 | Discharge Letters | Clinical Back Office | Wintel | Homegrown | Partners in Care VB.NET web application | AVM | Retire | eCW | Wintel
17 | EZCare | Clinical Management | Wintel |  | Care management and scheduling for payor adult day care | AVM | Retire | eCW | Wintel
18 | Foothold | Clinical Management | SaaS |  | EMR application used by Comprehensive Care Mgmt. Dept. | AVM | Retire | eCW | Wintel
19 | HC Plus | Clinical Management | SaaS |  | Provides scheduling and compliance, payroll and billing component | AVM | Retire | eCW | Wintel
20 | IVANS | Clinical Back Office | SaaS | COTS | IVANS value added network services for insurance eligibility and claims verification | AVM | Retire | eCW | Wintel
21 | MD Orders Tracking/Master Log Continues Clients | Clinical Management | Wintel | Homegrown | Partners in Care VB.NET web application | AVM | Retire | SAM | SaaS
22 | Nurse Assessment | Clinical Back Office | Mainframe (Sandata) | Homegrown | Partners in Care VB.NET web application | AVM | Retire | eCW | Wintel
23 | OPS | Clinical Management | Mainframe | Homegrown | Ordering for payor and Paraprofessional disciplines | AVM | Retire | eCW | Wintel
24 | Partners in Care Schedule | Clinical Management | Wintel |  | Provides in home clinical staff | AVM | Retire | eCW | Wintel
25 | PCRS Host | Clinical Management | Mainframe | Homegrown | Patient Care Record Suite | AVM | Retire | eCW | Wintel
26 | Service Charge Processing (SCP) | Clinical Back Office | Mainframe | Homegrown | Processes payments for visits made by both per diem clinicians, clinicians who are employees of vendors, paraprofessional services, supplies and DME and PERS. | AVM | Retire | eCW | Wintel
27 | Suncoast | Clinical Management | Wintel | COTS | EMR application used by Hospice. Determine work hours for Hospice staff. Interface with CellTrak application | AVM | Retire | eCW | Wintel